## INTRO
Project Name | : | NIU SAFE APP
Names | : | GOPICHAND BUDDI
ADIVENKATA NAGA SAIVINEELA KARNATAPU
HEMANTH POTHINENI
Course No | : | OMIS 690
Date | : | 2021-02-22

## WBS
NIU SAFE APP
1: configration updates
1.1: student live tracking
1.2: providnig previous crime onformation
1.3: update suspects information
1.4: case filing chat update
1.5: settings and message baseses
1.6: chatbot and agentchat
2: user interface
2.1: interactive design
2.2: visual design
2.3: develp design document
2.4: create fresh interface
3: creating database storage
3.1: creating pysical steps of datamodel
3.2: store NIU students data
3.3: database normalization
3.4: database requiment specification
4: deployment
4.1: test cases
4.2: creating new twst cases
4.3: software test
4.4: end test report
4.5: go live

## RTM
Req# | Requirement Description | Source/Requestor | Business justification | WBS Task | Test Strategy | Status
1 | configration updates | GOPICHAND BUDDI | Development of the app and updates and some drawbacks. |  | Updates in NIU safe app which is necessary to develop and makes easier to use. | PROSSESING
2 | user interface | HEMANTH POTHINENI | Students and faculty can know information and files cases directly to authorities. | 2, 2.1, 2.2, 2.3, 2.4 | Performance of the app and Graphical user interface is done. | PROSSESING
3 | creating database storage | VINEELA | By storing the users data, the information can be accessed with ease and can also be used for the future purpose. | 3, 3.1, 3.1, 3.3, 3.4 | Database testing and specification requirements must be done. | PROSSESING
4 | deployment | GOPICHAND, HEMANTH, VINEELA | Once the app is approved by the university officials, the NIU safe app is deployed in production. | 4, 4.1, 4.2, 4.3, 4.4, 4.5 | Deploy the NIU safe app in production. | PROSSESING

## WBS DIS
WBS Code | WBS Name | WBS Description | Resources | Due date | Hours
1 | Configration updates | Necessary updates in the NIU safe app make it more user friendly and safe for the students and faculty. | Gopichand Buddi | 2022-02-02
1.1 | Student live tracking | Live tracking of the students will help to save them when they are in danger. | Gopichand Buddi | 2022-02-09
1.2 | Providing previous crime information | Safe app displays the information of the people who have criminal records in the university region. | Gopichand Buddi | 2022-02-16
1.3 | Update suspects information | Suspects' information in the university region will updated on time to time. | Gopichand Buddi | 2022-02-23
1.4 | Case filing chat update | Users can directly chat with the police to file a case. | Gopichand Buddi | 2022-03-02
1.5 | Settings and message baseses | Settings and message chatbox will update and develop with more options. | Gopichand Buddi | 2022-03-09
1.6 | Chatbot and agentchat | Chatbot is the automated reply by the computer to clarify their doubts and agent chat is to file the cases on people. | Gopichand Buddi | 2022-03-23
2 | User interface | Faculty and students of NIU interact with the computer software and complaint about their problems and also get data. | Hemanth Pothineni | 2022-02-23
2.1 | Interactive design | The interaction with users are automated replies by software, when users raise a complaint it will send to higher authorities. | Hemanth Pothineni | 2022-03-02
2.2 | Visual design | The visual design of the app is top-notch with clear images and high picture quality. | Hemanth Pothineni | 2022-03-09
2.3 | Develop design document | The documentation design is highly secured and stored in the database of NIU. | Hemanth Pothineni | 2022-03-30
2.4 | Create fresh interface | A fresh interface will be more user-friendly and guide the users to signup. | Hemanth Pothineni | 2022-04-05
3 | Creating database storage | Data is necessary to be preserved through database storage so that the information of staff and students are maintained. | Vineela | 2022-02-16
3.1 | Creating pysical steps of datamodel | Physical steps indicates proper structuring of the models. | Vineela | 2022-03-02
3.2 | Store NIU students data | The data of all the students with the app has been retrieved to protect them in case of emergencies. | Vineela | 2022-03-09
3.3 | Database normalization | This implies meaningful arrangement of data model designs which help in data redundancy. | Vineela | 2022-03-30
3.4 | Database requiment specification | In order to define the collected files and data, it is necessaru to generate the database specification by using program coding. | Vineela | 2022-04-05
4 | Deployment | Deployment refers to a test run of the NIU safe app without any errors and data leakage. | Gopichand Buddi, Hemanth, Vineela | 2022-04-06
4.1 | Test cases | A test case is used to check if various components of a system are working properly and to ensure that the system meets all applicable standards, guidelines, and customer requirements. | Gopichand Buddi, Hemanth, Vineela | 2022-04-11
4.2 | Creating new test cases | When modifications are to be done, new test cases have been developed. | Gopichand Buddi, Hemanth, Vineela | 2022-04-18
4.3 | Software test | Inspect the test run of NIU safe app code without bugs and errors. | Gopichand Buddi, Hemanth, Vineela | 2022-04-23
4.4 | End test report | To indicate final completion, the Final Test Report is a written report that summarizes the outcomes, processes, and paperwork. | Gopichand Buddi, Hemanth, Vineela | 2022-04-29
4.5 | Go live | Once the app is approved by the University officials, NIU safe app will be deployed. | Gopichand Buddi, Hemanth, Vineela | 2022-05-04