## Sheet1
Project Name | : | NIU SAFE APP
Names | : | GOPICHAND BUDDI
ADIVENKATA NAGA SAIVINEELA KARNATAPU
HEMANTH POTHINENI
Course No | : | OMIS 690
Date | : | 2022-04-06

## Sheet2
Task Table
Tasks | Activity +AA2:J4 | Start Date | Finish Date | Predecessor | PERT = O+4ML+P/6 | Duration | Optimistic | Pessimistic | Most Likely
A | Ideation And Discovery | 2022-02-02 | 2022-02-07 | PS | 5.833 | 6 | 5 | 6 | 6
B | Development And Testing | 2022-02-08 | 2022-02-24 | A | 17 | 17 | 15 | 19 | 17
C | Develop App Screens | 2022-02-28 | 2022-03-04 | B | 4.66 | 5 | 3 | 5 | 5
D | Configration Update | 2022-03-05 | 2022-03-15 | C | 10.16 | 10 | 9 | 12 | 10
E | Intigration With Backend | 2022-03-18 | 2022-03-25 | D | 8 | 8 | 7 | 9 | 8
F | Coding And Aesign | 2022-03-28 | 2022-04-04 | E | 7.66 | 8 | 6 | 8 | 8
G | Creating Database Storage | 2022-04-05 | 2022-04-13 | F | 9.16 | 9 | 8 | 11 | 9
H | Creating New Test Casess | 2022-04-15 | 2022-04-21 | G | 7.16 | 7 | 6 | 9 | 7
I | Testing Of App | 2022-04-25 | 2022-04-28 | H | 3.66 | 4 | 2 | 4 | 4
J | End Test Report | 2022-04-29 | 2022-05-03 | I | 4.83 | 5 | 4 | 5 | 5
K | Publishing App | 2022-05-04 | 2022-05-04 | J | 1.16 | 1 | 1 | 2 | 1